## Worklogs
Issue Key | Issue summary | Hours | Work date | Username | Full name | Period | Account Key | Account Name | Activity Name | Component | All Components | Version Name | Issue Type | Issue Status | Project Key | Project Name | Work Description | Parent Key | Reporter | External Hours | Billed Hours | Issue Original Estimate | Issue Remaining Estimate
AL-929 | Insurance - Self Insured | 3 | 2015-11-06 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-929 |  | uzi | 0 | 3 | 2 | 0
AL-847 | claims search - filter only new | 3 | 2015-11-06 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Bug | Resolved | AL | AllMeds | Working on issue AL-847 |  | uzi | 0 | 3 | 4 | 1
AL-679 | Process | 1 | 2015-11-06 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 1 | 0 | 0
AL-841 | Support new commands for linked searhes in readonly mode. | 0.75 | 2015-11-06 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Sub-task | Resolved | AL | AllMeds | Working on issue AL-841 | AL-830 | dvasylenko | 0 | 0.75 | 2 | 1.25
AL-918 | Exception in global searches due to field hashing | 2.5 | 2015-11-06 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-918 |  | dvasylenko | 0 | 2.5 | 3 | 0.5
AL-677 | Tech Architecture | 1 | 2015-11-06 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-677 |  | vtymchik | 0 | 1 |  | 0
AL-827 | write-off dialog | 0.5 | 2015-11-06 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Sub-task | Resolved | AL | AllMeds | Working on issue AL-827 | AL-826 | uzi | 0 | 0.5 | 16 | 0
AL-944 | Fix Visual for Outstanding A/R by Insurance Class widget | 0.5 | 2015-11-06 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Bug | Ready for QA | AL | AllMeds | Working on issue AL-944 |  | uzi | 0 | 0.5 | 0.5 | 0
AL-704 | Automatic Account number | 2 | 2015-11-06 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Bug | Reopened | AL | AllMeds | Working on issue AL-704 |  | uzi | 0 | 2 | 2 | 0
AL-924 | Claims - error when trying to sort by insurance name | 0.5 | 2015-11-06 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-924 |  | uzi | 0 | 0.5 | 1 | 0.5
AL-933 | Fix Patient 56 very long loading | 0.75 | 2015-11-06 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Sub-task | Verified by QA | AL | AllMeds | Working on issue AL-933 | AL-932 | vtymchik | 0 | 0.75 | 1 | 0
AL-876 | patient - fix patient payments tab | 0.5 | 2015-11-06 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Bug | Ready for QA | AL | AllMeds | Working on issue AL-876 |  | uzi | 0 | 0.5 | 1 | 0
AL-876 | patient - fix patient payments tab | 1 | 2015-11-05 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Bug | Ready for QA | AL | AllMeds | Working on issue AL-876 |  | uzi | 0 | 1 | 1 | 0
AL-679 | Process | 2 | 2015-11-04 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 2 | 0 | 0
AL-679 | Process | 1.5 | 2015-11-05 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 1.5 | 0 | 0
AL-859 | payments - Unapplied payments | 4 | 2015-11-05 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Bug | Ready for QA | AL | AllMeds | Working on issue AL-859 |  | uzi | 0 | 4 | 4 | 0
AL-766 | Create custom WAF form (just layout, widgets, hide/show logic) | 1 | 2015-11-05 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Sub-task | Ready for QA | AL | AllMeds | Working on issue AL-766 | AL-763 | vtymchik | 0 | 1 | 12 | 1
AL-933 | Fix Patient 56 very long loading | 0.25 | 2015-11-05 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Sub-task | Verified by QA | AL | AllMeds | Working on issue AL-933 | AL-932 | vtymchik | 0 | 0.25 | 1 | 0
AL-906 | visits in 'Charges Finalized' status don't appear in the visit search screen | 0.25 | 2015-11-05 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-906 |  | uzi | 0 | 0.25 | 0.5 | 0
AL-836 | Write-Off limit | 0.25 | 2015-11-05 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Sub-task | Ready for QA | AL | AllMeds | Working on issue AL-836 | AL-826 | uzi | 0 | 0.25 | 8 | 1.75
AL-925 | Deep Review of Scheduling Module | 0.5 | 2015-11-05 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | New Feature | Open | AL | AllMeds | Working on issue AL-925 |  | uzi | 0 | 0.5 | 8 | 7.5
AL-677 | Tech Architecture | 1 | 2015-11-05 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-677 |  | vtymchik | 0 | 1 |  | 0
AL-679 | Process | 1 | 2015-11-05 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 1 | 0 | 0
HF-70 | External Website Scheduling | 0.5 | 2015-11-05 | vtymchik | Vadim Tymchik | 1115 |  |  | Sprint 2014/12/11 |  |  | Sprint 2014/12/11 | Task | Closed | HF | HF | Working on issue HF-70 |  | tabitha td | 0 | 0.5 |  | 0
AL-866 | Dashboard - wire claim aging widget | 2 | 2015-11-05 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Task | Ready for QA | AL | AllMeds | Working on issue AL-866 |  | uzi | 0 | 2 | 3 | 0
AL-920 | claims - change buttons | 0.16667 | 2015-11-05 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Task | Verified by QA | AL | AllMeds | Working on issue AL-920 |  | uzi | 0 | 0.16667 | 0.25 | 0.083333
AL-927 | map Insurance to claim | 0.25 | 2015-11-05 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-927 |  | uzi | 0 | 0.25 | 0.5 | 0.25
AL-929 | Insurance - Self Insured | 1 | 2015-11-05 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-929 |  | uzi | 0 | 1 | 2 | 0
AL-922 | insurance - re-arrange authorization screen | 0.33333 | 2015-11-05 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Task | Reopened | AL | AllMeds | Working on issue AL-922 |  | uzi | 0 | 0.33333 | 0.5 | 0.16667
AL-747 | Create main Payment Details Screen | 0.25 | 2015-11-05 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Sub-task | Ready for QA | AL | AllMeds | Working on issue AL-747 | AL-65 | dvasylenko | 0 | 0.25 | 6 | 0
AL-679 | Process | 1.3333 | 2015-11-05 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 1.3333 | 0 | 0
AL-921 | patient - change address | 0.16667 | 2015-11-05 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-921 |  | uzi | 0 | 0.16667 | 0.25 | 0.083333
AL-679 | Process | 1 | 2015-11-05 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 1 | 0 | 0
AL-775 | patient widget - Alerts | 1.5 | 2015-11-05 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Sub-task | Verified by QA | AL | AllMeds | Working on issue AL-775 | AL-772 | uzi | 0 | 1.5 | 4 | 0
AL-679 | Process | 1 | 2015-11-02 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 1 | 0 | 0
AL-679 | Process | 1 | 2015-11-05 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 1 | 0 | 0
AL-679 | Process | 1 | 2015-11-04 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 1 | 0 | 0
AL-679 | Process | 1 | 2015-11-03 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 1 | 0 | 0
AL-902 | change status when receiving | 1 | 2015-11-05 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Sub-task | Ready for QA | AL | AllMeds | Working on issue AL-902 | AL-811 | uzi | 0 | 1 | 1 | 0
AL-901 | new SIU message to update visit | 3 | 2015-11-03 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Sub-task | Ready for QA | AL | AllMeds | Working on issue AL-901 | AL-811 | uzi | 0 | 3 | 8 | 1
AL-901 | new SIU message to update visit | 4 | 2015-11-02 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Sub-task | Ready for QA | AL | AllMeds | Working on issue AL-901 | AL-811 | uzi | 0 | 4 | 8 | 1
AL-899 | fix MSH messages | 2 | 2015-11-02 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Sub-task | Ready for QA | AL | AllMeds | Working on issue AL-899 | AL-811 | uzi | 0 | 2 | 2 | 0
AL-900 | weird char in HL7 messages | 1 | 2015-11-04 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Sub-task | Ready for QA | AL | AllMeds | Working on issue AL-900 | AL-811 | uzi | 0 | 1 | 2 | 1
AL-679 | Process | 0.5 | 2015-11-04 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 0.5 | 0 | 0
AL-914 | new admin screen | 4.5 | 2015-11-04 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Task | Reopened | AL | AllMeds | Working on issue AL-914 |  | uzi | 0 | 4.5 | 3 | 0.5
AL-914 | new admin screen | 1 | 2015-11-05 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Task | Reopened | AL | AllMeds | Working on issue AL-914 |  | uzi | 0 | 1 | 3 | 0.5
AL-866 | Dashboard - wire claim aging widget | 1 | 2015-11-04 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Task | Ready for QA | AL | AllMeds | Working on issue AL-866 |  | uzi | 0 | 1 | 3 | 0
AL-897 | add Claim lines to claim summary screen | 2 | 2015-11-05 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Task | Verified by QA | AL | AllMeds | Working on issue AL-897 |  | uzi | 0 | 2 | 8 | 0
AL-889 | Reports - A/R aging | 6 | 2015-11-04 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Bug | Ready for QA | AL | AllMeds | Working on issue AL-889 |  | uzi | 0 | 6 | 8 | 0
AL-679 | Process | 0.66667 | 2015-11-04 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 0.66667 | 0 | 0
AL-889 | Reports - A/R aging | 2 | 2015-11-03 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Bug | Ready for QA | AL | AllMeds | Working on issue AL-889 |  | uzi | 0 | 2 | 8 | 0
AL-803 | Template - applying template is slow | 7 | 2015-11-04 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-803 |  | uzi | 0 | 7 | 16 | 0.25
AL-873 | dashboard - wire Outstanding A/R widget | 3 | 2015-11-04 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Bug | Ready for QA | AL | AllMeds | Working on issue AL-873 |  | uzi | 0 | 3 | 1 | 0
AL-677 | Tech Architecture | 0.5 | 2015-11-04 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-677 |  | vtymchik | 0 | 0.5 |  | 0
AL-679 | Process | 0.5 | 2015-11-04 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 0.5 | 0 | 0
AL-837 | Appointment details screen glitches | 1.5 | 2015-11-04 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-837 |  | kleontovich | 0 | 1.5 | 1.5 | 0
AL-771 | connect fee schedule to a visit | 1 | 2015-11-04 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-771 |  | uzi | 0 | 1 | 8 | 0.5
AL-898 | add PV1 to ADT | 2 | 2015-11-03 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Sub-task | Ready for QA | AL | AllMeds | Working on issue AL-898 | AL-811 | uzi | 0 | 2 | 4 | 0
AL-898 | add PV1 to ADT | 2 | 2015-11-04 | dvasylenko | Dmytro Vasylenko | 1115 |  |  | AllMeds |  |  |  | Sub-task | Ready for QA | AL | AllMeds | Working on issue AL-898 | AL-811 | uzi | 0 | 2 | 4 | 0
AL-803 | Template - applying template is slow | 3 | 2015-11-03 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-803 |  | uzi | 0 | 3 | 16 | 0.25
AL-885 | Add filters | 1 | 2015-11-04 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Sub-task | Verified by QA | AL | AllMeds | Working on issue AL-885 | AL-873 | dvasylenko | 0 | 1 | 3 | 0
AL-875 | Fix dashboard filters | 0.5 | 2015-11-04 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-875 |  | vtymchik | 0 | 0.5 | 8 | 0
AL-917 | patient/visit - insurance tab show all insurances for all patients | 0.5 | 2015-11-04 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-917 |  | uzi | 0 | 0.5 | 0.5 | 0
AL-912 | claims - add value to Insurance Type drop-down | 0.16667 | 2015-11-04 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-912 |  | uzi | 0 | 0.16667 |  | 0
AL-908 | visit screen - make Lines tab default | 2 | 2015-11-03 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Task | Verified by QA | AL | AllMeds | Working on issue AL-908 |  | uzi | 0 | 2 | 2 | 0
AL-679 | Process | 2 | 2015-11-03 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 2 | 0 | 0
AL-916 | Performance optimization for widgets & reports | 4 | 2015-11-03 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Task | Open | AL | AllMeds | - Created large database (about 1 mil of rows for all most important tables like transactionLines, visitLines, products and proportional amount for other tables). - Outstanding AR widget and Claims Payments widget are optimized to run on this amount of data |  | kleontovich | 0 | 4 |  | 0
AL-679 | Process | 0.5 | 2015-11-03 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 0.5 | 0 | 0
AL-775 | patient widget - Alerts | 7.5 | 2015-11-03 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Sub-task | Verified by QA | AL | AllMeds | Working on issue AL-775 | AL-772 | uzi | 0 | 7.5 | 4 | 0
AL-677 | Tech Architecture | 1 | 2015-11-03 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-677 |  | vtymchik | 0 | 1 |  | 0
AL-679 | Process | 0.5 | 2015-11-03 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 0.5 | 0 | 0
AL-747 | Create main Payment Details Screen | 3 | 2015-11-03 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Sub-task | Ready for QA | AL | AllMeds | Working on issue AL-747 | AL-65 | dvasylenko | 0 | 3 | 6 | 0
AL-915 | Visits.FinalizedDate | 1 | 2015-11-03 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Sub-task | Verified by QA | AL | AllMeds | Working on issue AL-915 | AL-830 | igolodnitsky | 0 | 1 | 1 | 0
AL-897 | add Claim lines to claim summary screen | 1 | 2015-11-03 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Task | Verified by QA | AL | AllMeds | Working on issue AL-897 |  | uzi | 0 | 1 | 8 | 0
AL-679 | Process | 0.66667 | 2015-11-03 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 0.66667 | 0 | 0
AL-897 | add Claim lines to claim summary screen | 7 | 2015-11-02 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Task | Verified by QA | AL | AllMeds | Working on issue AL-897 |  | uzi | 0 | 7 | 8 | 0
AL-885 | Add filters | 2 | 2015-11-02 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Sub-task | Verified by QA | AL | AllMeds | Working on issue AL-885 | AL-873 | dvasylenko | 0 | 2 | 3 | 0
AL-873 | dashboard - wire Outstanding A/R widget | 1 | 2015-11-02 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Bug | Ready for QA | AL | AllMeds | Working on issue AL-873 |  | uzi | 0 | 1 | 1 | 0
AL-803 | Template - applying template is slow | 1.5 | 2015-11-02 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-803 |  | uzi | 0 | 1.5 | 16 | 0.25
AL-895 | Separate popups for different transaction types. | 1.5 | 2015-11-02 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Sub-task | Closed | AL | AllMeds | Working on issue AL-895 | AL-826 | uzi | 0 | 1.5 | 2 | 0.5
AL-836 | Write-Off limit | 6 | 2015-11-02 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Sub-task | Ready for QA | AL | AllMeds | Working on issue AL-836 | AL-826 | uzi | 0 | 6 | 8 | 1.75
AL-906 | visits in 'Charges Finalized' status don't appear in the visit search screen | 0.25 | 2015-11-02 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Bug | Verified by QA | AL | AllMeds | Working on issue AL-906 |  | uzi | 0 | 0.25 | 0.5 | 0
AL-891 | Create claim - don't show lines twice | 1 | 2015-11-02 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Bug | Closed | AL | AllMeds | Working on issue AL-891 |  | uzi | 0 | 1 | 1 | 0
AL-679 | Process | 1 | 2015-11-02 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 1 | 0 | 0
AL-884 | change appointment reason logic | 0.5 | 2015-11-02 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Task | Closed | AL | AllMeds | Working on issue AL-884 |  | uzi | 0 | 0.5 | 3 | 0
AL-880 | Claim widget feedback | 0.25 | 2015-11-02 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Bug | Closed | AL | AllMeds | Working on issue AL-880 |  | uzi | 0 | 0.25 | 1 | 0.25
AL-524 | create claims | 0.25 | 2015-11-02 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Sub-task | Closed | AL | AllMeds | Working on issue AL-524 | AL-56 | uzi | 0 | 0.25 | 6 | 0
AL-677 | Tech Architecture | 0.75 | 2015-11-02 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-677 |  | vtymchik | 0 | 0.75 |  | 0
AL-679 | Process | 0.75 | 2015-11-02 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 0.75 | 0 | 0
AL-888 | reports dashboard | 7.3333 | 2015-11-02 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Task | Closed | AL | AllMeds | Working on issue AL-888 |  | uzi | 0 | 7.3333 | 8 | 0
AL-679 | Process | 0.66667 | 2015-11-02 | igolodnitsky | Igor Golodnitsky | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 0.66667 | 0 | 0
AL-679 | Process | 0.66667 | 2015-11-02 | mkotsievsky | Mikhail Kotsievsky | 1115 |  |  | AllMeds |  |  |  | Story | Open | AL | AllMeds | Working on issue AL-679 |  | uzi | 0 | 0.66667 | 0 | 0
AL-905 | Exception if Save PriceList without Office | 0.25 | 2015-11-02 | Kleontovich | Kirill Leontovich | 1115 |  |  | AllMeds |  |  |  | Bug | Closed | AL | AllMeds | Working on issue AL-905 |  | dvasylenko | 0 | 0.25 | 0.25 | 0
AL-839 | create view to Dev Express - Pivot Grid | 4 | 2015-11-01 | vtymchik | Vadim Tymchik | 1115 |  |  | AllMeds |  |  |  | Sub-task | Ready for QA | AL | AllMeds | Working on issue AL-839 | AL-838 | uzi | 0 | 4 | 24 | 0

## People
Name | Username | Worked | Billed | Planned | Required | Progress | 2015-11-01 | 2015-11-02 | 2015-11-03 | 2015-11-04 | 2015-11-05 | 2015-11-06 | 2015-11-07 | 2015-11-08 | 2015-11-09 | 2015-11-10 | 2015-11-11 | 2015-11-12 | 2015-11-13 | 2015-11-14 | 2015-11-15 | 2015-11-16 | 2015-11-17 | 2015-11-18 | 2015-11-19 | 2015-11-20 | 2015-11-21 | 2015-11-22 | 2015-11-23 | 2015-11-24 | 2015-11-25 | 2015-11-26 | 2015-11-27 | 2015-11-28 | 2015-11-29 | 2015-11-30
Kirill Leontovich | Kleontovich | 26.25 | 26.25 | 0 | 168 | 16 | 0 | 7.75 | 8 | 7.5 | 2.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mikhail Kotsievsky | mkotsievsky | 30 | 30 | 0 | 168 | 18 | 0 | 8 | 8 | 8 | 5.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dmytro Vasylenko | dvasylenko | 25.1667 | 25.1667 | 0 | 168 | 15 | 0 | 7 | 6 | 4 | 6.1667 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Igor Golodnitsky | igolodnitsky | 34.5 | 34.5 | 0 | 168 | 21 | 0 | 7.6667 | 7.6667 | 6.8333 | 5.3333 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uzi Livneh | uzi | 0 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vadim Tymchik | vtymchik | 36.5 | 36.5 | 0 | 168 | 22 | 4 | 9.25 | 4.5 | 8 | 4.75 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Planned
Issue Key | Issue summary | Hours | Plan Date | Username | Full name | Period | Account Key | Account Name | Activity Name | Component | All Components | Version Name | Issue Type | Issue Status | Project Key | Project Name | Parent Key | Reporter | Issue Original Estimate | Issue Remaining Estimate | Plan Status | Plan Description