## Timesheet Report (5)
Project | Type | Key | Title | Assignee | Original Estimate | Status | Story Points | Date | Username | Time Spent (h) | Comment
AllMeds | Sub-task | AL-524 | AL-56> create claims | vtymchik(vtymchik) | 6h | Closed |  | 2015-11-02 10:00 | Vadim Tymchik | 0.25 | Working on issue AL-524
AllMeds | Story | AL-677 | Tech Architecture | vtymchik(vtymchik) | 0h | Open |  | 2015-11-02 10:00 | Vadim Tymchik | 0.75 | Working on issue AL-677
AllMeds | Story | AL-677 | Tech Architecture | vtymchik(vtymchik) | 0h | Open |  | 2015-11-03 10:00 | Vadim Tymchik | 1 | Working on issue AL-677
AllMeds | Story | AL-677 | Tech Architecture | vtymchik(vtymchik) | 0h | Open |  | 2015-11-04 10:00 | Vadim Tymchik | 0.5 | Working on issue AL-677
AllMeds | Story | AL-677 | Tech Architecture | vtymchik(vtymchik) | 0h | Open |  | 2015-11-05 10:00 | Vadim Tymchik | 1 | Working on issue AL-677
AllMeds | Story | AL-677 | Tech Architecture | vtymchik(vtymchik) | 0h | Open |  | 2015-11-06 10:00 | Vadim Tymchik | 1 | Working on issue AL-677
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-02 10:00 | Mikhail Kotsievsky | 0.667 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-02 | Igor Golodnitsky | 0.667 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-02 10:00 | Vadim Tymchik | 0.75 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-02 | Kirill Leontovich | 1 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-02 10:00 | Dmytro Vasylenko | 1 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-03 | Igor Golodnitsky | 0.667 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-03 10:00 | Vadim Tymchik | 0.5 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-03 10:00 | Mikhail Kotsievsky | 0.5 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-03 | Kirill Leontovich | 2 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-03 10:00 | Dmytro Vasylenko | 1 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-04 10:00 | Vadim Tymchik | 0.5 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-04 | Igor Golodnitsky | 0.667 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-04 10:00 | Mikhail Kotsievsky | 0.5 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-04 10:00 | Dmytro Vasylenko | 1 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-04 | Kirill Leontovich | 2 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-05 10:00 | Dmytro Vasylenko | 1 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-05 10:00 | Mikhail Kotsievsky | 1 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-05 | Igor Golodnitsky | 1.333 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-05 10:00 | Vadim Tymchik | 1 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-05 | Kirill Leontovich | 1.5 | Working on issue AL-679
AllMeds | Story | AL-679 | Process | dvasylenko(dvasylenko) | 0h | Open |  | 2015-11-06 | Igor Golodnitsky | 1 | Working on issue AL-679
AllMeds | Bug | AL-704 | Automatic Account number | dvasylenko(dvasylenko) | 2h | Reopened |  | 2015-11-06 10:00 | Dmytro Vasylenko | 2 | Working on issue AL-704
AllMeds | Sub-task | AL-747 | AL-65> Create main Payment Details Screen | igolodnitsky(igolodnitsky) | 6h | Ready for QA |  | 2015-11-03 | Igor Golodnitsky | 3 | Working on issue AL-747
AllMeds | Sub-task | AL-747 | AL-65> Create main Payment Details Screen | igolodnitsky(igolodnitsky) | 6h | Ready for QA |  | 2015-11-05 | Igor Golodnitsky | 0.25 | Working on issue AL-747
AllMeds | Sub-task | AL-766 | AL-763> Create custom WAF form (just layout, widgets, hide/show logic) | vtymchik(vtymchik) | 12h | Ready for QA |  | 2015-11-05 10:00 | Vadim Tymchik | 1 | Working on issue AL-766
AllMeds | Bug | AL-771 | connect fee schedule to a visit | Kleontovich(kleontovich) | 8h | Verified by QA |  | 2015-11-04 | Kirill Leontovich | 1 | Working on issue AL-771
AllMeds | Sub-task | AL-775 | AL-772> patient widget - Alerts | mkotsievsky(mkotsievsky) | 4h | Verified by QA |  | 2015-11-03 10:00 | Mikhail Kotsievsky | 7.5 | Working on issue AL-775
AllMeds | Sub-task | AL-775 | AL-772> patient widget - Alerts | mkotsievsky(mkotsievsky) | 4h | Verified by QA |  | 2015-11-05 10:00 | Mikhail Kotsievsky | 1.5 | Working on issue AL-775
AllMeds | Bug | AL-803 | Template - applying template is slow | vtymchik(vtymchik) | 16h | Verified by QA |  | 2015-11-02 | Kirill Leontovich | 1.5 | Working on issue AL-803
AllMeds | Bug | AL-803 | Template - applying template is slow | vtymchik(vtymchik) | 16h | Verified by QA |  | 2015-11-03 10:00 | Vadim Tymchik | 3 | Working on issue AL-803
AllMeds | Bug | AL-803 | Template - applying template is slow | vtymchik(vtymchik) | 16h | Verified by QA |  | 2015-11-04 10:00 | Vadim Tymchik | 7 | Working on issue AL-803
AllMeds | Sub-task | AL-827 | AL-826> write-off dialog | vtymchik(vtymchik) | 16h | Resolved |  | 2015-11-06 10:00 | Vadim Tymchik | 0.5 | Working on issue AL-827
AllMeds | Sub-task | AL-836 | AL-826> Write-Off limit | vtymchik(vtymchik) | 8h | Ready for QA |  | 2015-11-02 10:00 | Vadim Tymchik | 6 | Working on issue AL-836
AllMeds | Sub-task | AL-836 | AL-826> Write-Off limit | vtymchik(vtymchik) | 8h | Ready for QA |  | 2015-11-05 10:00 | Vadim Tymchik | 0.25 | Working on issue AL-836
AllMeds | Bug | AL-837 | Appointment details screen glitches | mkotsievsky(mkotsievsky) | 1.5h | Verified by QA |  | 2015-11-04 10:00 | Mikhail Kotsievsky | 1.5 | Working on issue AL-837
AllMeds | Sub-task | AL-839 | AL-838> create view to Dev Express - Pivot Grid | mkotsievsky(mkotsievsky) | 24h | Ready for QA |  | 2015-11-01 09:00 | Vadim Tymchik | 4 | Working on issue AL-839
AllMeds | Sub-task | AL-841 | AL-830> Support new commands for linked searhes in readonly mode. | vtymchik(vtymchik) | 2h | Resolved |  | 2015-11-06 10:00 | Vadim Tymchik | 0.75 | Working on issue AL-841
AllMeds | Bug | AL-847 | claims search - filter only new | igolodnitsky(igolodnitsky) | 4h | Resolved |  | 2015-11-06 | Igor Golodnitsky | 3 | Working on issue AL-847
AllMeds | Bug | AL-859 | payments - Unapplied payments | dvasylenko(dvasylenko) | 4h | Ready for QA |  | 2015-11-05 10:00 | Dmytro Vasylenko | 4 | Working on issue AL-859
AllMeds | Task | AL-866 | Dashboard - wire claim aging widget | mkotsievsky(mkotsievsky) | 3h | Ready for QA |  | 2015-11-04 10:00 | Mikhail Kotsievsky | 1 | Working on issue AL-866
AllMeds | Task | AL-866 | Dashboard - wire claim aging widget | mkotsievsky(mkotsievsky) | 3h | Ready for QA |  | 2015-11-05 10:00 | Mikhail Kotsievsky | 2 | Working on issue AL-866
AllMeds | Bug | AL-873 | dashboard - wire Outstanding A/R widget | Kleontovich(kleontovich) | 1h | Ready for QA |  | 2015-11-02 | Kirill Leontovich | 1 | Working on issue AL-873
AllMeds | Bug | AL-873 | dashboard - wire Outstanding A/R widget | Kleontovich(kleontovich) | 1h | Ready for QA |  | 2015-11-04 | Kirill Leontovich | 3 | Working on issue AL-873
AllMeds | Bug | AL-875 | Fix dashboard filters | mkotsievsky(mkotsievsky) | 8h | Verified by QA |  | 2015-11-04 10:00 | Mikhail Kotsievsky | 0.5 | Working on issue AL-875
AllMeds | Bug | AL-876 | patient - fix patient payments tab | Kleontovich(kleontovich) | 1h | Ready for QA |  | 2015-11-05 | Kirill Leontovich | 1 | Working on issue AL-876
AllMeds | Bug | AL-876 | patient - fix patient payments tab | Kleontovich(kleontovich) | 1h | Ready for QA |  | 2015-11-06 | Kirill Leontovich | 0.5 | Working on issue AL-876
AllMeds | Bug | AL-880 | Claim widget feedback | Kleontovich(kleontovich) | 1h | Closed |  | 2015-11-02 | Kirill Leontovich | 0.25 | Working on issue AL-880
AllMeds | Task | AL-884 | change appointment reason logic | Kleontovich(kleontovich) | 3h | Closed |  | 2015-11-02 | Kirill Leontovich | 0.5 | Working on issue AL-884
AllMeds | Sub-task | AL-885 | AL-873> Add filters | Kleontovich(kleontovich) | 3h | Verified by QA |  | 2015-11-02 | Kirill Leontovich | 2 | Working on issue AL-885
AllMeds | Sub-task | AL-885 | AL-873> Add filters | Kleontovich(kleontovich) | 3h | Verified by QA |  | 2015-11-04 | Kirill Leontovich | 1 | Working on issue AL-885
AllMeds | Task | AL-888 | reports dashboard | mkotsievsky(mkotsievsky) | 8h | Closed |  | 2015-11-02 10:00 | Mikhail Kotsievsky | 7.333 | Working on issue AL-888
AllMeds | Bug | AL-889 | Reports - A/R aging | igolodnitsky(igolodnitsky) | 8h | Ready for QA |  | 2015-11-03 | Igor Golodnitsky | 2 | Working on issue AL-889
AllMeds | Bug | AL-889 | Reports - A/R aging | igolodnitsky(igolodnitsky) | 8h | Ready for QA |  | 2015-11-04 | Igor Golodnitsky | 6 | Working on issue AL-889
AllMeds | Bug | AL-891 | Create claim - don't show lines twice | Kleontovich(kleontovich) | 1h | Closed |  | 2015-11-02 | Kirill Leontovich | 1 | Working on issue AL-891
AllMeds | Sub-task | AL-895 | AL-826> Separate popups for different transaction types. | vtymchik(vtymchik) | 2h | Closed |  | 2015-11-02 10:00 | Vadim Tymchik | 1.5 | Working on issue AL-895
AllMeds | Task | AL-897 | add Claim lines to claim summary screen | igolodnitsky(igolodnitsky) | 8h | Verified by QA |  | 2015-11-02 | Igor Golodnitsky | 7 | Working on issue AL-897
AllMeds | Task | AL-897 | add Claim lines to claim summary screen | igolodnitsky(igolodnitsky) | 8h | Verified by QA |  | 2015-11-03 | Igor Golodnitsky | 1 | Working on issue AL-897
AllMeds | Task | AL-897 | add Claim lines to claim summary screen | igolodnitsky(igolodnitsky) | 8h | Verified by QA |  | 2015-11-05 | Igor Golodnitsky | 2 | Working on issue AL-897
AllMeds | Sub-task | AL-898 | AL-811> add PV1 to ADT | dvasylenko(dvasylenko) | 4h | Ready for QA |  | 2015-11-03 10:00 | Dmytro Vasylenko | 2 | Working on issue AL-898
AllMeds | Sub-task | AL-898 | AL-811> add PV1 to ADT | dvasylenko(dvasylenko) | 4h | Ready for QA |  | 2015-11-04 10:00 | Dmytro Vasylenko | 2 | Working on issue AL-898
AllMeds | Sub-task | AL-899 | AL-811> fix MSH messages | dvasylenko(dvasylenko) | 2h | Ready for QA |  | 2015-11-02 10:00 | Dmytro Vasylenko | 2 | Working on issue AL-899
AllMeds | Sub-task | AL-900 | AL-811> weird char in HL7 messages | dvasylenko(dvasylenko) | 2h | Ready for QA |  | 2015-11-04 10:00 | Dmytro Vasylenko | 1 | Working on issue AL-900
AllMeds | Sub-task | AL-901 | AL-811> new SIU message to update visit | dvasylenko(dvasylenko) | 8h | Ready for QA |  | 2015-11-02 10:00 | Dmytro Vasylenko | 4 | Working on issue AL-901
AllMeds | Sub-task | AL-901 | AL-811> new SIU message to update visit | dvasylenko(dvasylenko) | 8h | Ready for QA |  | 2015-11-03 10:00 | Dmytro Vasylenko | 3 | Working on issue AL-901
AllMeds | Sub-task | AL-902 | AL-811> change status when receiving | dvasylenko(dvasylenko) | 1h | Ready for QA |  | 2015-11-05 10:00 | Dmytro Vasylenko | 1 | Working on issue AL-902
AllMeds | Bug | AL-905 | Exception if Save PriceList without Office | Kleontovich(kleontovich) | 0.25h | Closed |  | 2015-11-02 | Kirill Leontovich | 0.25 | Working on issue AL-905
AllMeds | Bug | AL-906 | visits in 'Charges Finalized' status don't appear in the visit search screen | Kleontovich(kleontovich) | 0.5h | Verified by QA |  | 2015-11-02 | Kirill Leontovich | 0.25 | Working on issue AL-906
AllMeds | Bug | AL-906 | visits in 'Charges Finalized' status don't appear in the visit search screen | Kleontovich(kleontovich) | 0.5h | Verified by QA |  | 2015-11-05 10:00 | Vadim Tymchik | 0.25 | Working on issue AL-906
AllMeds | Task | AL-908 | visit screen - make Lines tab default | Kleontovich(kleontovich) | 2h | Verified by QA |  | 2015-11-03 | Kirill Leontovich | 2 | Working on issue AL-908
AllMeds | Bug | AL-912 | claims - add value to Insurance Type drop-down | igolodnitsky(igolodnitsky) | 0h | Verified by QA |  | 2015-11-04 | Igor Golodnitsky | 0.167 | Working on issue AL-912
AllMeds | Task | AL-914 | new admin screen | mkotsievsky(mkotsievsky) | 3h | Reopened |  | 2015-11-04 10:00 | Mikhail Kotsievsky | 4.5 | Working on issue AL-914
AllMeds | Task | AL-914 | new admin screen | mkotsievsky(mkotsievsky) | 3h | Reopened |  | 2015-11-05 10:00 | Mikhail Kotsievsky | 1 | Working on issue AL-914
AllMeds | Sub-task | AL-915 | AL-830> Visits.FinalizedDate | igolodnitsky(igolodnitsky) | 1h | Verified by QA |  | 2015-11-03 | Igor Golodnitsky | 1 | Working on issue AL-915
AllMeds | Task | AL-916 | Performance optimization for widgets & reports | Allmeds(allmeds) | 0h | Open |  | 2015-11-03 | Kirill Leontovich | 4 | - Created large database (about 1 mil of rows for all most important tables like transactionLines, visitLines, products and proportional amount for other tables). - Outstanding AR widget and Claims Payments widget are optimized to run on this amount of data
AllMeds | Bug | AL-917 | patient/visit - insurance tab show all insurances for all patients | Kleontovich(kleontovich) | 0.5h | Verified by QA |  | 2015-11-04 | Kirill Leontovich | 0.5 | Working on issue AL-917
AllMeds | Bug | AL-918 | Exception in global searches due to field hashing | vtymchik(vtymchik) | 3h | Verified by QA |  | 2015-11-06 10:00 | Vadim Tymchik | 2.5 | Working on issue AL-918
AllMeds | Task | AL-920 | claims - change buttons | igolodnitsky(igolodnitsky) | 0.25h | Verified by QA |  | 2015-11-05 | Igor Golodnitsky | 0.167 | Working on issue AL-920
AllMeds | Bug | AL-921 | patient - change address | dvasylenko(dvasylenko) | 0.25h | Verified by QA |  | 2015-11-05 10:00 | Dmytro Vasylenko | 0.167 | Working on issue AL-921
AllMeds | Task | AL-922 | insurance - re-arrange authorization screen | igolodnitsky(igolodnitsky) | 0.5h | Reopened |  | 2015-11-05 | Igor Golodnitsky | 0.333 | Working on issue AL-922
AllMeds | Bug | AL-924 | Claims - error when trying to sort by insurance name | vtymchik(vtymchik) | 1h | Verified by QA |  | 2015-11-06 10:00 | Vadim Tymchik | 0.5 | Working on issue AL-924
AllMeds | New Feature | AL-925 | Deep Review of Scheduling Module | vtymchik(vtymchik) | 8h | Open |  | 2015-11-05 10:00 | Vadim Tymchik | 0.5 | Working on issue AL-925
AllMeds | Bug | AL-927 | map Insurance to claim | igolodnitsky(igolodnitsky) | 0.5h | Verified by QA |  | 2015-11-05 | Igor Golodnitsky | 0.25 | Working on issue AL-927
AllMeds | Bug | AL-929 | Insurance - Self Insured | igolodnitsky(igolodnitsky) | 2h | Verified by QA |  | 2015-11-05 | Igor Golodnitsky | 1 | Working on issue AL-929
AllMeds | Bug | AL-929 | Insurance - Self Insured | igolodnitsky(igolodnitsky) | 2h | Verified by QA |  | 2015-11-06 | Igor Golodnitsky | 3 | Working on issue AL-929
AllMeds | Sub-task | AL-933 | AL-932> Fix Patient 56 very long loading | vtymchik(vtymchik) | 1h | Verified by QA |  | 2015-11-05 10:00 | Vadim Tymchik | 0.25 | Working on issue AL-933
AllMeds | Sub-task | AL-933 | AL-932> Fix Patient 56 very long loading | vtymchik(vtymchik) | 1h | Verified by QA |  | 2015-11-06 10:00 | Vadim Tymchik | 0.75 | Working on issue AL-933
AllMeds | Bug | AL-944 | Fix Visual for Outstanding A/R by Insurance Class widget | mkotsievsky(mkotsievsky) | 0.5h | Ready for QA |  | 2015-11-06 10:00 | Mikhail Kotsievsky | 0.5 | Working on issue AL-944
Total | [11 empty] | 151.917